## Slide 1: Summary & Planning Task 3.4.1
B. Nikolic
15/9/2016

## Slide 2: Task Contributions (whole of 3.4)
Partner | INAF | UCAM | LAPP | IAP | APC | CPPM | CEA | ASTRON | JIVE | INFN
Effort (PM) | 36 | 60 | 30 | 36 | 24 | 6 | 36 | 24 | 24 | 18
Contact | F. Pasian | B. Nikolic | P. Aubert |  | E. Chassande-Mottin |  | T. Stolarczyk | T. Dijkema | M. Kettenis | C. Bozza

## Slide 3: Upcoming Deliverables & Milestones
D.3.9 M24 (30th April 2017): Statistical Solvers Technology Benchmark Report
?Mid-term review?
D.3.17 M48 (30th April 2019): Release of software libraries
Contribution to final report (30th April 2019)

## Slide 4: Task 3.4.1 Description
Developing a collection of statistically robust and domain independent open source software libraries for data analysis and data mining on Peta-scale datasets. This will enable a sustained community-based effort towards excellent exploitation of all data generated by the ESFRI and pathfinder facilities. The initial set of libraries developed within this task are in particular:
Statistically robust approaches (Bayesian and likelihood analyses) to advance cross-matching between catalogues and transients detected via different instruments
Domain independent image analysis for simultaneous feature classification and extraction in multi-dimensional/multi-resolution data where the data are from multiple instruments.
Effective likelihood reconstruction methods and new graphical processing approaches (mainly for event-based and signal-based projects but not exclusively) optimised for newcomputing technologies and maximum efficiency.

## Slide 5: Missing partner contributions
Following partners do not appear in the deliverables table for our 1st milestone:
  IAP
  APC
  CPPM

## Slide 6: Planned deliverables within 3.4.1
Name | Short Description | Notes
SMART | Library of sparse methods for signal and image processing | 
PLIBS | Library of optimised low-level/elementary functions | 
MW-Inference | Source detection and classification for multi-wavelength data | 
StatPlanner | Planning statistical studies based on catalogues of observations and sources | 
VLBI in the cloud? | Cloud computing and minimal re-computation for CASA | Overlap with 3.4.2
AWImager2 | Imaging of radio-interferometric data with AW-projection. | 
CASAsynthesis | Base library for AWImager2 | 
DPPP? | Streaming framework for radio interferometric data | Overlap with 3.4.2
CORELib | Library of cosmic ray events | 
ROAst | Extension of the Root framework library for Astronomy | 
pLISA | Identification and Study of Astroparticles | 

## Slide 7: Analysis
Limited overlap
Potential synergies & reuse which we should investigate

## Slide 9: Issues
License compatibility: Are CeCILL and GPLv3 compatible?
Degree of re-engineering required: might be very substantial
Mix of programming languages
Benefits?
  Performance?
  Scalability?
  Maintainability?
Will analyse potential benefits in next milestone!

## Slide 10: Deliverable 3.9 “Statistical Solvers Technology Benchmark Report”
Report on efficiency, performance, scalability of statistical tools & libraries used in likelihood calculations
Should include at minimum:
  PLIBS, SMART, ROAST, MW-INFERENCE, AWIMAGER2, PLISA, STAT PLANNER
Comparison with existing software/approaches essential
Where new software is not yet functioning, a benchmark of existing technology in the relevant area is appropriate