## Slide 1: ASTERICS finances
Status period 1 and projection
for periods 2 and 3

## Slide 2: Budget in DoA
Chart: ASTERICS DoA budget (EUR)
| WP1 AMST | WP2 DECS | WP3 OBELICS | WP4 DADI | WP5 CLEOPATRA
Budget total (EUR) | 1216795 | 733221.5 | 6143415 | 4402125 | 2495637.5
Total: € 14.991.194
Chart: ASTERICS DoA budget (PM)
| WP1 AMST | WP2 DECS | WP3 OBELICS | WP4 DADI | WP5 CLEOPATRA
Budget total (person months) | 88 | 53 | 752 | 429 | 332
Total: 1 654 PM
66% budgeted for personnel
15% budgeted for other costs (mostly travel costs)
19% budgeted for indirect costs (25% flat rate)
Notes: These charts show the original budget of the project. Work packages 3 and 4 are the largest in spending costs and person months.
The largest part of the budget is reserved for personnel costs. The budget for other costs is mainly for travel costs.

## Slide 3: Financial report – at month 18
Chart: ASTERICS Actual PR1 (EUR)
| WP1 AMST | WP2 DECS | WP3 OBELICS | WP4 DADI | WP5 CLEOPATRA
Actual total (EUR) | 234073.3176 | 85902.2957 | 1004590.0785 | 901406.1413 | 913582.6275
Total: € 3.139.554
Progress in time: 38%
(18 out of 48 project months)
Actual spending at 18 months: 21%
Realization per work package:
WP1 19%
WP2 12%
WP3 16%
WP4 20%
WP5 37%
Notes: In November all partners reported on their spendings of the first 18 months.
The project was then at 38% of progress in time. The actual spendings reported, however, have reached 21%.
Compared to a linear spending profile, all work packages are underspending, except for WP5.
The actual spendings are lower than the planned spending curve. We will show that we can correct this in the second part of the project.

## Slide 4: DoA versus EAC
Chart: DoA vs. EAC (personnel costs)
| WP1 | WP2 | WP3 | WP4 | WP5
Budget DoA total (EUR) | 733436 | 315808 | 4006732 | 2627500 | 1804830
EAC total (EUR) | 610515.544 | 271872.738 | 3435548.2728 | 2478216.539 | 1821515.3127
Chart: DoA vs. EAC (person months)
| WP1 | WP2 | WP3 | WP4 | WP5
Budget DoA total (PM) | 88 | 53 | 752 | 429 | 332
EAC total (PM) | 83.91 | 46.41 | 716.0633 | 456.2268 | 329.8293
Notes: One year into the project, we asked all partners to provide us a revised budget on personnel costs: their Estimate to Complete (ETC) the project, based on contractual obligations known at that moment.
The charts above show the actual spendings of the first 18 months plus the ETC till the end of the project: the Estimate at Completion (EAC). Note: for personnel costs and person months only!

## Slide 5: Spending profiles personnel costs
Chart: ETC vs. Actual (personnel costs)
| 1 - 6 | 7 -12 | 13 - 18 | 19 - 24 | 25 - 30 | 31 - 36 | 37 - 42 | 43 - 48
ETC | 406207.1015 | 681795.4342 | 1078004.3141 | 1314963.5701 | 1372379.6501 | 1300681.1001 | 1337898.2341 | 1277995.6741
ACTUAL | 366951.0181 | 686495.3442 | 960303.8156
Chart: Spending curves (integral personnel costs)
| 1 - 6 | 7 -12 | 13 - 18 | 19 - 24 | 25 - 30 | 31 - 36 | 37 - 42 | 43 - 48
Spend plan | 406207.1015 | 1088002.5356 | 2166006.8498 | 3480970.4199 | 4853350.07 | 6154031.1702 | 7491929.4043 | 8769925.0784
Actuals | 366951.0181 | 1053446.3623 | 2013750.1778
Budget ceiling | 9488306 | 9488306 | 9488306 | 9488306 | 9488306 | 9488306 | 9488306 | 9488306
Spending profile in 6 months periods.
Cumulative costs towards end of project

## Slide 6: Spending profile work packages
Small dip for WP3 is caused by EAC of partners FAU (reduced their PM by half) and IFAE (finished work).
Chart: EAC - 6 monthly profile (person months)
| 1 - 6 | 7 -12 | 13 - 18 | 19 - 24 | 25 - 30 | 31 - 36 | 37 - 42 | 43 - 48
WP1 | 7.03 | 8.12 | 8.56 | 12.18 | 12.08 | 12.08 | 11.98 | 11.88
WP2 | 0.37 | 2.75 | 3.69 | 8.1 | 8.1 | 8 | 7.8 | 7.6
WP3 | 17.56 | 56.42 | 95.65 | 109.2667 | 113.1667 | 104 | 112.2 | 107.8
WP4 | 18.5429 | 27.0607 | 45.19 | 64.6515 | 71.58 | 73.6 | 78.268 | 77.3338
WP5 | 22.4198 | 44.7103 | 47.1739 | 56.9851 | 53.2851 | 41.2851 | 36.2851 | 27.6851
Chart: DoA vs. EAC (person months)
| 1 - 6 | 7 -12 | 13 - 18 | 19 - 24 | 25 - 30 | 31 - 36 | 37 - 42 | 43 - 48
WP1 | 7.03 | 15.15 | 23.71 | 35.89 | 47.97 | 60.05 | 72.03 | 83.91
WP2 | 0.37 | 3.12 | 6.81 | 14.91 | 23.01 | 31.01 | 38.81 | 46.41
WP3 | 17.56 | 73.98 | 169.63 | 278.8967 | 392.0633 | 496.0633 | 608.2633 | 716.0633
WP4 | 18.5429 | 45.6036 | 90.7936 | 155.4451 | 227.0251 | 300.6251 | 378.8931 | 456.2268
WP5 | 22.4198 | 67.1301 | 114.304 | 171.289 | 224.5741 | 265.8592 | 302.1442 | 329.8293
WP1 | 88
WP2 | 53
WP3 | 752
WP4 | 429
WP5 | 332
The dot at the end of the line represents the total budget on person months per work package according to the DoA.
Notes: The chart on the left shows the spending profile on person months per work package (per six month).
Note the relatively stable line till the end of the project for all work packages except WP5.
The first 18 months are the actual person months spent.
The chart to the right shows the cumulative progress in person months per work package.
The dot at the end of the line represents the total budget on person months per work package, as described in the DoA.
The first 18 months are the actual person months spent.
The rest of the lines are formed by the estimates that partners provided us.
Notice the steep lines for work packages 3 and 4, but also for work packages 1 and 2.
The steep lines pose a risk if staff cannot be allocated to the project till the end of the project, or if a staff member decides to leave an organization.

## Slide 7: Next steps
All partners will provide an updated ETC.
  If partners expect over- or underspending we will ask them to provide us with concrete actions, in close collaboration with the WP-leaders.
Our aim is to have a steeper spending profile
  Rather ramp down at the end of the project than have to speed up towards the end.
We monitor proposed actions and will continue to signal deviations.